## project
CS18010 Group
[11 empty] | Plan |  | Actual
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Day
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12
Initial Meeting | 1 | 1 | 1 | 2 | 100%
Resource Gathering | 2 | 6 | 2 | 8 | 100%
Slide Production | 3 | 5 | 4 | 7 | 100%
Follow Up Meeting | 10 | 1 | 10 | 1 | 100%
Final Meeting | 12 | 1 | 12 | 1 | 100%
Presentation Practice | 12 | 1 | 12 | 1 | 100%
Presentation | 12 | 1 | n/a | n/a | 0%